## ICSR
Task | Activity | Owner | Target Date | Status | Comment
Translate | Prompt optimization | Nithin | 2024-01-09 | In Progress | Prompt optimization & testing
| Prompt examples | Nithin | 2024-01-10 | Not Started
| Output parsing to Json | Nithin | 2024-01-10 | Not Started
| Developing API & Testing | Sowmya Narayanan | 2024-01-11 | Not Started
| Integration with UI | Sowmya Narayanan | 2024-01-11 | Not Started
| End to End Testing | Sowmya Narayanan | 2024-01-11 | Not Started
Entity Extraction From XML | Integration with UI | Sowmya Narayanan / Pranathi | 2024-01-09 | In Progress | Yet to test - Format of the API response changed as per the UI requirment
| End to End Testing |  | 2024-01-09 | In Progress | Yet to test - Format of the API response changed as per the UI requirment
Entity Extraction From Narrative | Integration with UI | Sowmya Narayanan / Pranathi | 2024-01-09 | In Progress | Yet to test - Format of the API response changed as per the UI requirment
| End to End Testing |  | 2024-01-09 | In Progress | Yet to test - Format of the API response changed as per the UI requirment
Narrative Generation | Integration with UI | Sowmya Narayanan / Pranathi | 2024-01-09 | In Progress | Yet to test - Format of the API response changed as per the Model requirment
| End to End Testing |  | 2024-01-09 | In Progress | Yet to test - Format of the API response changed as per the Model requirment
Product Code | Integration with UI | Sowmya Narayanan / Pranathi | 2024-01-09 | Completed
| End to End Testing |  | 2024-01-09 | Completed
Landing Page | UI development | Pranathi | 2024-01-11 | Not Started
New UI for ICSR | Reviewing the Figma wireframes | Sai
Deployment | Developing the app | Sai
| Testing the app | Sai / Team
Mistral | Creating endpoint for mistral & meditron | Eswar | 2024-01-08 | Not Started

## LLM Playground
Task | Activity | Owner | Target Date | Status | Comment
LLM Playground | Developing the UI | Sombir | 2024-01-10
| Developing the backend code to inference the model with user input | Eswar | 2024-01-10 | In Progress
| API development | Eswar | 2024-01-10 | Yet to start
| Integration with UI | Eswar / Pranathi | 2024-01-10 | Yet to start
| End to End testing | Eswar | 2024-01-10 | Yet to start
Deployment | Development | Sai |  | Yet to start
| Testing the app in dev | Sai / Team |  | Yet to start

## Theia
Task | Activity | Owner | Target Date | Status | Comment
Doc QnA Chatbot | Creating API for like, dislike | Nithin
| Creating API for comment | Nithin
| Creating API for regenerate the response(need to discuss) | Nithin
| Testing Feedback: Displaying same document names 5 times - UI error - doc names are not coming as it is. it is getting trimmed. | Pranathi
| Testing Feedback: Ref document names are getting duplicated. if multiple doc are available in same document, then show document name only once | Pranathi
| Testing Comments: Retrieval vector DB: similarity docs are coming even for irrelevant context like when we asking about cars. | Eswar |  | NA
| Testing Feedback: Auto scroll to the bottom of the page after generating the answer | Pranathi
| Testing Feedback: don't show document links for the answer that don't known by model | Eswar
| Testing Feedback: Enabling conversational buffer memory | Eswar | Sprint 2
| Testing Feedback: implementing chain of thoughts | Eswar | Sprint 2
| Testing Feedback: change temp to min value & no of docs to 3 | Eswar
NSQL QnA Chatbot | Checking OpenAI VOX API feasibility with Langchain | Eswar / Sai
| R&D on best open source models for text to SQL generation | Eswar |  | NA
| Creating the Custom LLM with VOX API to support langchain frame work | Eswar
| Going through langchain wrapper | Eswar |  | NA
| LLama2 for integration for SQL agents | Eswar |  | NA
Testing with open source models like mistral /
| Apply for git access for langchain wrapper | Eswar
| Sprint planning | Eswar
UI Changes | Developing the landing page | Pranathi
| Login & Authentication | Pranathi

## Dataiku
Task | Activity | Owner | Target Date | Status | Comment

## KG UI
Task | Activity | Owner | Target Date | Status | Comment
KG UI | Filter Integration
Update Graph based on Filter Selection
Neo4J Api integration based on filter selection
Show Node Properties on Hover of node
Update UI header

## Gen
Task | Activity | Owner | Target Date | Status | Comment
Code review (before deploying) | Modular coding | Eswar
Creating Backups | code | Eswar
| prompts | Eswar
Code references | model eval | Eswar
| fine tuning and RLFT | Eswar
| Dockerization & deployment in Linux | Eswar
| Movies backup files to S3 | Eswar
| coping backup from s3 to Linux instance | Eswar
| git & CICD pipelines | Eswar
R&D Tasks | Integrating DB for storing chat feedbacks by user & logs
Reducing latency in LLM response
Streaming output
Consistency in output format - Json
timeout error -
Token limit
user session context specific response based on previous chat
reasoning or analytics over rag approach
understating last year/last quarter terminologies
LLM should restrict irrelevant context or abuse words.
Implementing thought process for complex queries which involves analytics
token length for schema
handling complex queries
visualizations
analysis on query (SQL) response
R&D Topics | Multi-task LLMs
Best Open source LLMs for NSQL, translation, medical domain specific
Learning | lama index
AWS certification